## COMMENT
CAPSTONE PROJECT 2 ACCOMPLISHMENT AND CONSULTATION FORM
INSTRUCTION: List all the activities, improvements or accomplishments that has been made in your Capstone Project Documentation and System/Prototype. This form may be reproduced as you go along with your Capstone Project. This form should be submitted to your Capstone Project Adviser every week.
Capstone Project Title: WEB-BASED PIGGERY MANAGEMENT SYSTEM WITH MOBILE-BASED QR CODE SCANNER FOR RVM HOG FARM IN LAMBA, BANGA SOUTH COTABATO
Week Number: 2
Date: Feb. 22, 2023
|  | ACTIVITY/ACCOMPLISHMENT | PERCENTAGE OF COMPLETION | REMARKS/ COMMENTS/ SUGGESTIONS/ DELIVERABLES and DUE DATE | COMPLIANCE
F. System |  |  | 25% | Put a asterisk on the required text field, Fix the alert/notification, Fix the sorting bug.
a. Module 1- User Management
|  | Add User |  | Working | complied
|  | Update |  | Working | complied
|  | Cancel/Reset |  | Working | complied
|  | View List of Users |  | Working | complied
|  | Cancel |  | Working | complied
| b. Module 2- Cage Management |  |  | Filter the capacity of each cages,
|  | Add/Create |  | Working | complied
|  | Update |  | Working | complied
|  | View |  | Remove the dropdown
|  | Cancel |  | Working | complied
| c. Module 3- Pig Management |  |  | Not working
Add
Update
View
Cancel
| d. Module 3- Inventory Management |  |  | Not working
Add
Update
View
Cancel
e. Module 4- Module Name
Add
Update
View
Cancel
Prepared by:
| 1 | Surname, Fname,MI
| 2 | Surname, Fname,MI
| 3 | Surname, Fname,MI
| 4 | Surname, Fname,MI
Checked by: |  |  |  | Approved by by:
Engr. Leila B. Guerrero, PhD
|  | Capstone Project Adviser |  | Capstone Project Coordinator
|  | Date Signed: |  | Date Signed: